## Table
PERSONALIZED FINANCIAL GOAL-ACHIEVEMENT & INCOME-GROWTH PLATFORM
SAGE: 8-Week Plan
PHASE | KEY ACTIVITIES | START WEEK | DURATION (WEEKS) | EXPECTED OUTCOME | START | DURATION
User Foundation | Login/sign-up User onboarding Basic user profile | 1 | 2 | User account & financial profile | 1 | 2
Money Dashboard | Weekly/monthly/yearly spending Income & savings overview Spending alerts & important updates | 2 | 3 | Functional financial dashboard | 2 | 3
Smart Opportunities | Side-hustle recommendation Personalized earning opportunities | 3 | 3 | Side-hustle recommendation system | 3 | 3
Saving Benefits | Coupons, offers & discounts Expiry-based notifications Money-saving opportunities | 4 | 3 | Coupon & saving module | 4 | 3
SAGE Intelligence | AI/chatbot integration Financial guidance Personalized goal suggestions Spending-based insights | 4 | 3 | Smart financial assistant | 4 | 3
Goal & Bill Reminders | Future financial goals Bill reminders Saving reminders | 5 | 3 | Reminder & goal system | 5 | 3
Testing & Refinement | Bug fixing UI improvements Performance checks | 6 | 3 | Stable working prototype | 6 | 3
Buffer & User Testing | Final user testing Feedback collection Final improvements & validation | 7 | 2 | Final validated SAGE prototype | 7 | 2